## G702
TO CONTRACTOR: |  |  | PROJECT: |  |  |  | APPLICATION NO: |  | 1 | DISTRIBUTION TO:
Pustola & Associates Engineers Constructors |  |  | ABC Project |  |  |  | APPLICATION DATE |  | 2017-01-20 |  | OWNER
185 Meadow Street |  |  | 1 Sample Lane |  |  |  | PERIOD TO: |  | 2017-01-20
Naugatuck, CT 06770 |  |  | Naugatuck, CT 06770 |  |  |  | PROJECT NO: |  |  |  | ARCHITECT
FROM SUBCONTRACTOR: | [6 empty] | CONTRACT DATE: |  |  | X | CONTRUCTION MANAGER
ABC Subcontractor
123 Testing Rd
Naugatuck, CT 06770
SUBCONTRACTORS APPLICATION FOR PAYMENT
Application is made for payment, as shown below, in connection with the Contract. | [5 empty] | CERTIFICATE FOR PAYMENT In accordance with the Contract Documents, based on on-site observations and the data comprising this application, the subcontractor certifies to the Owner that to the best of their knowledge, information and belief the Work has been progressed as indicated, the quality of the Work is in accordance with the Contract Documents, and the subcontractor is entitled to payment of the amount certified.
Continuation Sheet, AIA Document G703, is attached.
1. ORIGINAL CONTRACT SUM……………………………………………………. |  |  |  | $ | 100000 | SUBCONTRACTOR:
2. NET CHANGE BY CHANGE ORDERS………………………………………….. |  |  |  | $ | 300
3. CONTRACT SUM TO DATE (Line 1 ± 2)……………………………………….. |  |  |  | $ | 100300 | By: ____________________________________________________________ |  |  |  | Date: ___________________
4. TOTAL COMPLETED & STORED TO DATE (Column G on 703)...…………. |  |  |  | $ | 2300
5. RETAINAGE: | [5 empty] | AMOUNT CERTIFIED |  | $ | 2200
a. | 0.05 | % of Completed Work $ | 100 |  |  | (Attach explanation if amount certified differs from the amount applied for. Initial all figured on this
| (Column D + E on G703) |  |  |  |  | Application and on the Continuation Sheet that changed to conform to the amount certified.)
b. | 0.05 | % of Stored Material $ | 0
(Column I on G703)
TOTAL RETAINAGE (total in column I of G703)……………….………………. |  |  |  | $ | 100
APPLICATION FOR PAYMENT CHECKLIST TO BE COMPLETED BY CONTRUCTION ADVISOR
6. TOTAL EARNED LESS RETAINAGE (Line 4 less Line 5 Total)…………. |  |  |  | $ | 2200
7. LESS PREVIOUS CERTIFICATES FOR PAYMENT (Line 6 from prior).. |  |  |  | $ | 0 | P&A Project Accountant: Check list below for completeness. If items are missing, contact Subcontractor for completion before payment is released.
8. CURRENT PAYMENT DUE…………………………………………………….. |  |  |  | $ | 2200
9. BALANCE TO FINISH, INCLUDING RETAINAGE (Line 3 less Line 6)…. |  |  |  | $ | 98100 | Original Application |  |  | ____
[6 empty] | Original Continuation Sheet |  |  | ____
[6 empty] | Conditional Lien Release |  |  | ____
[6 empty] | Current Insurance Cert. on hand |  |  | ____
CHANGE ORDER SUMMARY |  |  | ADDITIONS |  | DEDUCTIONS
Total change orders approved in previous months:
Notes for Subcontractor:
Total change approved this month: |  |  | 0 |  | 0 | Only bill for change orders that have been approved by Construction Advisor. Billing for unapproved change orders may result in invoice being kicked back for revision and eliminated from current billing to owner.
|  |  | 0 |  | 0
|  | TOTALS: |  |  |  | Attach all appropriate Supplier and Subcontractor lien releases with completed Application for Payment.
NET CHANGES by Change Orders: |  |  | 0
AIA DOCUMENT G702/CMa · APPLICATION AND CERTIFICATION FOR PAYMENT · CONSTRUCTION MANAGER-ADVISER EDITION · 1992 EDITION · AIA · ©1992 | [11 empty] | G702/CMa-1992

## G703
| CONTINUATION SHEET |  |  |  | . | AIA DOCUMENT G703
| AIA Document G702, APPLICATION AND CERTIFICATION FOR PAYMENT |  |  |  |  | APPLICATION NO: |  | 1
[6 empty] | APPLICATION DATE: |  | 2016-10-01
[6 empty] | PERIOD TO: |  | 2016-10-01
ARCHITECT'S PROJECT NO:
| A | B | C | D | E | F | G |  | H | I
| ITEM NO. | DESCRIPTION OF WORK | SCHEDULED VALUE | WORK COMPLETED |  | MATERIAL STORED | TOTAL COMPLETED AND STORED TO DATE | % | BALANCE TO FINISH | RETAINAGE (5%)
|  |  |  | FROM PREVIOUS APPLICATION | THIS PERIOD
| 1 | AIA Contract Amount - DIV 09 - Flooring - Carpet | 40000 |  | 1000 | 0 | 1000 | 2.5% | 39000 | 50
| 2 | AIA Contract Amount - DIV 09 - Flooring - Tile | 60000 |  | 1000 | 0 | 1000 | 1.667% | 59000 | 50
| 3 |  |  |  |  | 0 | 0 | #DIV/0! | 0 | 0
| 4 |  |  |  |  | 0 | 0 | #DIV/0! | 0 | 0
|  | TOTAL CONTRACT: | 100000 | 0 | 2000 | 0 | 2000 | 2% | 98000 | 100
CHANGE ORDERS:
| CO#1 | Extra tile in Womens Bathroom | 100 |  | 100 | 0 | 100 | 100% | 0 | 0
| CO#2 | Extra tile in service area | 200 |  | 200 | 0 | 200 | 100% | 0 | 0
CO#3
CO#4
CO#4
CO#5
0 | TOTAL CHANGE ORDERS: |  | 300 | 0 | 300 | 0 | 300 | 100% | 0 | 0
| TOTAL: |  | 100300 | 0 | 2300 | 0 | 2300 | 2.293% | 98000 | 100